## Skills Matrix
Skills Matrix
Tasks | Business Knowledge | Management | Design Systems | Design Spaces | Install Equipment | Construction
Specify requirements | x | x | x | x
Contract with vendor |  | x
Design update |  |  | x |  |  | x
Install equipment |  |  |  |  | x
Design spaces |  |  | x |  |  | x
Construct | [5 empty] | x
Test |  |  | x |  | x
People needed | 1 | 1 | 2 | 1 | 8 | 5
Weekly rate | 5000 | 4000 | 2000 | 5000 | 2400 | 4000
Estimated weeks | 2 | 4 | 4 | 1 | 6 | 6
Estimate (based on hours) | 5000 | 6500 | 5000 | 5000 | 115000 | 224000
Total Labor Costs | 360500