## Sheet1
Project | Conference Center Project
Last updated
Risk ID | Description | Trigger | Probability | Impact | Priority | Owner | Response | Expected Results | Status | Notes
1 | New technology doesn't work. | Testing | High | High | 1 | Brett | Mitigate | Prototype determines whether technology works. | Watch
2 | New technology requires more remodeling than expected. | Design | Medium | Medium | 4 | Jennifer | Contingency funds | Extra funds cover the remodeling cost. | Plan implemented
3 | New technology isn't available. | Placing equipment order | Medium | High | 2 | Brett | Avoid | Build schedule to provide time for obtaining equipment. | Watch
4 | Technology becomes obsolete before project is finished. | Release of radical new technology | Medium | High | 3 | Brett | Transfer | Contract with vendor includes clause to replace any obsolete technology. | Watch
5 | There are cost overruns. | Design | Medium | Medium | 5 | Mark | Mitigate | Identify alternatives to contain cost. | Watch