## CR Log
Change Request Log
Last updated: | 2011-12-05
CR ID | Requestor | Change Request Summary | Impact Estimate | Status | Actual Impact
001 | Jennifer | Revise remodel of conference center reception desk. | Increase cost. | Approved | $10,000 additional cost
002 | Brett | Delay installation by 3 weeks due to availability. | Delay schedule. | Under evaluation
003 | Jennifer | Add built-in panels in rooms. | Delay schedule and increase cost. | Rejected
004 | Brett | Change equipment brand for higher dependability. | Increase cost. | Under review